## Sheet1
Priority | Description of Mitigation Project | Goal for Hazards Mitigated | Mitigation Goals Achieved | Funding Source | Jurisdiction (Location) | Agency Responsible for Implementation | Estimated Costs | Status |  |  |  | Timeframe to Complete
[8 empty] | New | Ongoing | Deferred | If Deferred Why?
The projects located in this color are completed projects.
| Purchase and install a countywide telephone emergency notification system. | All Hazards | Yes | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management | N/A | In 2016- Franklin County Sheriffs office discontinued the "Code Red" notification system. Franklin County Emergency Management has started using and maintaining Nixle. The State is going to a state wide notification system and using Everbirdge- Nixle is a subsidiary of the Everbrige notification.
| Installation of hydrologic monitoring data collecting gauges on the Ochlockonee, Crooked, New and Apalachicola Rivers. | Floods | Yes | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management | N/A | The hydrologic monitoring gauges have been installed and are collecting data. Gauge installation at the Abercrombie Boat Ramp will occur once the ramp is rebuilt. The gauge has been purchased. Contact Preble Rish to install
| Reduce flooding by replacing culverts and improving cross drains at Mill Road, McIntyre Road, Jeff Sanders Road, Crooked River Road, Brickyard Road, and New River Road. | Floods | Yes | HMGP | All jurisdictions in Franklin County. | Franklin County Road Department | N/A | As of November 2012, the status of this stormwater project was the culverts were replaced and the improvement cross drain project was completed. The construction continued through 2013 and was funded through the HMGP.
| Install an updated water pump system in selected areas of Eastpoint. | All Hazards | Yes | CDBG | City of Eastpoint | Franklin County Sold Waste | TBD | A new system and well on twin Lakes Road was completed in the 2012 - 2013 timeframe. In addition two new vacuum stations was completed. . The project will be completed in September of 2016. The Well#1 will be retired and they will begin using Well #4.
| Emergency Operations Center Wind Retrofit | All Hazards, Hurricanes, Tropical Storms, Tornadoes, and High Winds | Yes | HMGP | City of Apalachicola | Franklin County Emergency Management | A important project and a critical facility for Franklin County. The EOC was awarded a HMGP grant to complete the wind retrofit project. The project was completed in the 1st quarter of 2015. The project description: Protected the entire envelope of the Franklin County Emergency Operations Center by designing and constructing a new hip roof and installing high velocity accordion shutters on the windows and installation of a roll down shutter on the access door of the EOC. The total cost for the mitigation project was: $94,943. This project will be moved to the completed mitigation project list at the next LMS meeting.
| Franklin County Jail Wind Retrofit. | All Hazards, Hurricanes, Tropical Storms, Tornadoes, and High Winds | Yes | HMGP | Town of Eastpoint | Franklin County Emergency Management | A important project and a critical facility for Franklin County. In addition, the jail is a back-up facility for the EOC. The Franklin County Jail was awarded a HMGP grant to complete the wind retrofit project. The project was completed in the 3rd quarter of 2015 and is waiting for final inspection from the State of Florida. The project description: Installed a new retrofit Metal Frame/Metal Roof Assembly over the Jail’s Administration Building, and a new Membrane Roof System over the Jail Facility House. In addition provided protection of all windows and doors of the entire structure. The total cost for the mitigation project was: $729,267. This project will be moved to the completed mitigation project list at the next LMS meeting.
1 | Update and enhance all communications equipment throughout the county | All Hazards | No | TBD | All jurisdictions | Franklin County Sheriff /Volunteer Fire Department/Franklin County Emergency Management/FC Road Dept/ Solid Waste | TBD | X | All Agencies are evaluating/ discussing options for interoperal communications through out the county. |  |  | Within 5 year
2 | Build a new EOC in central Franklin County possible location off of Hwy 65 | All Hazards | No | TBD | All jurisdictions in Franklin County. | FCEM/FCBOCC | TBD | Franklin County is looking at possible BP funds for building a new Multi-Agency Building. |  |  |  | Within a five-year timeframe.
3 | Install Weather/ Water and Wind Gauges applied to all bridges and in various points aroud Franklin County | All Hazards | No | TBD | All jusridictions | Franklin County Emergency Management/ DOT/ FCSO | TBD | This is a new project. Franklin County EM is actively working on placing a Wind Gauge on St George Island Bridge. DOT/Weather Stem are assisting in this project. |  |  |  | Within five-year timeframe
4 | Institute Flag system/Display board for beaches | All Hazards | No | TBD | Franklin County | DEP /FCEM/FC PARKS AND REC/ STATE PARK | TBD | X |  |  |  | Within five-year timeframe
5 | Mitigate storm damage caused by flooding on Alternate US 98 (Gulf Avenue, CR 30A South) and SE 12th Street in Carrabelle. | Floods | No | HMGP, and possible funds through BP. | City of Carrabelle | Franklin County Road Department | TBD | Studies have been completed by the Carrabelle ECT and the priority is funding for this project. It is on the priority list for appeal to BP if funding becomes available. The goal would be install additional culverts and conduct a restoration of the wetland area known as "the frog pond." |  |  |  | Within a five-year timeframe.
6 | Replace the components on the Eastpoint sewer lift station. | All Hazards | No | TBD | Eastpoint Water And Sewer District | Eastpoint Water & Sewer District | 300000 | This is a critical mitigation project for the Town of Eastpoint. This sewer lift station serves the county jail and landfill. The components need to be replaced in order for the system to function properly. Currently funding is being sought. |  |  |  | Within a one-year timeframe
7 | Reduce flooding in the Rio Vista area by installing a drainage system on the north side of the road into Cow Creek and the Ochlockonee River. | Floods | No | TBD | Unincorporated Franklin County | Franklin County Road Department/ Florida Forestry Service | TBD |  |  | x | Funding, need to evaluate drainage study | Within a five-year timeframe.
8 | Continue to plant vegetation along the county's coastal region to reduce erosion, enhance the formation of sand dunes and to protect roads from washouts. | Coastal Erosion | No | Various | All jurisdictions in Franklin County. | Franklin County Emergency Management | TBD |  | There has been progress on planting vegetation on the coastal regions of the county, however this is an on-going project that will continue to improve through the years. Anita from DEP will provide EM with an update. This is an ongoing project. |  |  | Within a five-year timeframe.
9 | Work with the Florida Forest Service on evaluating the defensible space on all the critical facilities throughout the county. | Wildfires | No | HMGP | All jurisdictions in Franklin County | Franklin County Emergency Management/ Florida Forest Service | N/A |  | The Franklin County EM Director sent specifics to the local Florida Forest Service.Florida Forest Service will provide the information on the defensible space on critical facilites. Ongoing Project |  |  | Within a one-year timeframe
10 | Work with the Florida Forest Service and develop and participate in the Community Wildfire Protection Plans (CWPP) to reduce wildfire risks within the Wildland-Urban Interface. And inform the public of the Firewise building and landscape design principles and the Ready, Set, Go program. | Wildfires | No | Florida Forestry Service | All jurisdictions in Franklin County. | Franklin County Emergency Management/ Florida Forest Service | N/A |  | x |  |  | Ongoing
11 | Work with the Florida Forest Service in offering forest protection education in the county's schools. | Widfires | No | Florida Forestry Service | All jurisdictions in Franklin County. | Florida Forest Service | N/A | Florida Forest Service has secured a scholarship for 20,000 a year for a graduate Franklin County School graduate further education in Forestry. Agriculture class and FFS continually provides Forest Protection education to all Franklin County Students. Summer program 2 students spent 3 days a week working in the Forest Service |  |  |  | Ongoing
12 | Install generators at 3 lift stations in Eastpoint- | All Hazards | No | TBD | Eastpoint Water And Sewer District | Eastpoint Water and Sewer District | TBD | x |  |  |  | Within a five-year timeframe.
13 | Identify the critical facilities in the county and review the hazards that could have a negative impact on them after a severe storm event. Evaluate on incorporating and relevant data into the GIS system. | All Hazards | No | N/A | All jurisdictions in Franklin County. | Franklin County EM and Franklin County Property Appraisers office | N/A | All critical facilities have been identified and GPS coordinates are completed. Surge maps with 911 data and base study is currently being completed by the ARPC.
14 | Improve efforts in debris removal of dead, dying or diseased trees and braches next to road and highways. | All Hazards | No | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management/ Duke Energy/ Transfield/ FC Road Department | N/A |  | x | Duke Energy maintains the power lines. Transfield has done work on Bluff Road and the Westend of the county. |  | Ongoing
15 | Protect and improve functioning of wetlands and waterways by control or elimination of invasive plants. | Coastal and Riverine Erosion | No | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management/ ANEER | TBD | Anita wth ANEER is contiually working with residents on Evasive Plants and controlling the spread. Next class will be helod Sept 15, 2016. Clint Davis with the Florida Forest Service has information and they distbiurse information about controlling evasive plants in our area. |  |  |  | Ongoing
16 | Protect County Road 370 (Alligator Point Road) from hurricane storm surge. | Hurricanes, Tropical Storms, Storm Surge | No | FEMA funding | Unincorporated Franklin County - Alligator Point | Franklin County Road Department | TBD | The county is currently working on relocating two road areas with FEMA funds. The work extends from Tom Roberts Drive to Harbor Circle and areas of Harry Morrison and Island Drive. The county has filed for a time extension for the project as part of the project is in litigation. This is an on-going project for the county. |  |  |  | Within a five-year timeframe.
17 | Reduce or prevent stormwater flooding in Apalachicola in the following areas: 24th and 25th Avenues, 8th through 10th Streets between J and G, and on US Highway 98 and 12th and 16th Streets. | Floods, Storm Surge | No | TBD | City of Apalachicola | City of Apalachicola Road Dept | TBD | This drainage improvement project is on the DOT 5-year capital project list. The DOT and Preble-Rish have agreed on a resurfacing project on US 98 through Apalachicola and estimated to be complete in 2014. The installation of buffer boxes are currently in progress. Some work has been done on 10th Street. The EM Director will get with the City and DOT for a status on the project. An update on the costs will be available at the next LMS meeting |  |  |  | Within a one-year timeframe
18 | Construct a new Fire Station in Alligator Point. | All Hazards | No | TBD | Unincorporated Franklin County - Alligator Point | Alligator Point Fire Department/ FCEM | TBD | The property has been purchased to construct a new fire station. Updates on funding will become available at the next meeting. No representative was available for update |  |  |  | Within a five-year timeframe.
19 | Identify all flood prone properties and disaster hazard zones to improve the emergency response time and data collection on damage assessment through the county GIS system. | Floods, Storm Surge | No | TBD | All jurisdictions in Franklin County. | FC Planning and Zoning/ Franklin County Appraiser's Office. | TBD | Franklin County is currently working on a project with grant funds to identfy all flood prone areas in the County.
20 | Develop and deliver Disaster Resistant programs for the business and residential communities on "how to prepare" for future disasters | All Hazards | Yes | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management | N/A |  | x | The Emergency Management office delivers ongoing programs and distributes materials on how to prepare for future disasters to the residential and business community. NOAA gave some money for this project and the ARPC is developing a program for businesses.This is an ongoing project. Em contiunally educates all Franklin County Residents in being Disaster ready
21 | Conduct Community Emergency Response Team (CERT) training for the Franklin County residents. | All Hazards | Yes | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management | N/A |  | x | Franklin County has a CERT group and continues to provide CERT training. This is an on-going program for the county.
22 | Retrofit the FSU Marine Lab buildings. | Hurricanes, Tropical Storms, Tornadoes, and High Winds | No | HMGP | Unincorporated Franklin County - St. Teresa | FSU Marine Lab | TBD |  | x | FSU Marine Lab has other buildings in that can benefit from Wind Retrofit
23 | Storm Water Project for Carrabelle- | Flood | No | TBD | City of Carrabelle | City of Carrabelle | TBD | X |  |  |  | Within five-year timeframe
24 | Raise the Pine Log Bridge Road area on Highway 67 on both sides in Franklin and Liberty Counties. | All Hazards | No | TBD | Unincorporated Franklin County | Franklin County Road Department | TBD |  | x | Need to determine what Liberty County is doing … both counties have to agree on raising the road |  | Within a five-year timeframe.
25 | Identify public and private school facilities that are in need of a wind retrofit. | Hurricanes, Tropical Storms, Tornadoes, and High Winds | No | TBD | All jurisdictions in Franklin County. | Franklin County Emergency Management Franklin County School Board | N/A |  |  | x | Funding | Within a five-year timeframe.
26 | Perform mitigation on efforts on residence homes against severe hurricanes, high winds , tropical storms, tornadoes and storm surge on low/moderate income owner occupied homes | Hurricanes, Tropical Storms, Tornadoes, High Winds, and Storm Surge | No | RCMP Funds | All jurisdictions in Franklin County. | Franklin County Emergency Management | TBD |  | x | Franklin County is currently working on a Residential Construction Mitigation Program for Franklin County residents- Ongoing Project
27 | Perform a study on the effects of severe hurricanes, high winds, tropical storms, tornadoes and storm surge on businesses that perform essential services to the community. | Hurricanes, Tropical Storms, Tornadoes, High Winds, and Storm Surge | No | TBD | All jurisdictions in Franklin County. | Franklin County Emergency Management | TBD |  |  | x | ARPC got a grant to complete this project. EM Director to follow up and get a status. | Within a five-year timeframe.
28 | Install sirens at various points throughout the county | Tornadoes & High Winds | No | TBD | All jurisdictions in Franklin County | Franklin County Emergency Management | TBD | A siren company has already mapped out locations to place the sirens throughout the county. |  |  |  | Within five-year timeframe
29 | Install tornado shelters throughout the county | Tornadoes & High Winds | No | TBD | All jurisdictions in Franklin County | Franklin County Emergency Management | TBD |  |  | x | Funding | Within a five-year timeframe.
30 | Build a new Wastewater Treatment Plant in Eastpoint. | All Hazards | No | TBD | Franklin County-Eastpoint | Eastpoint Water and Sewer District | TBD | X |  |  |  | Within five-year timeframe
31 | Acquire, relocate or elevate repetitive damaged structures throughout the county. | Floods, Storm Surge | No | TBD | All jurisdictions in Franklin County. | Franklin County Emergency Management | N/A |  |  | x | Funding | Within a five-year timeframe.
The mitigation projects in this color were deleted by the LMS Committee/Workgroup.
| Retrofit the Carrabelle City Hall Complex. | Hurricanes, Tropical Storms, Tornadoes, and High Winds | No | HMGP | City of Carrabelle | City of Carrabelle | TBD | This project was deleted at the August 2016 LMS meeting due to lack of funding and possible relocation of Carrabelle City Hall
| Inspect septic tanks for low-income homeowners and abate failing systems. | Floods | No | N/A | All jurisdictions in Franklin County. | N/A | N/A | This project was deleted at the November 2013 LMS meeting.
| Purchase and install smoke alarms in low income homes. | Wildfires | No | N/A | All jurisdictions in Franklin County. | N/A | N/A | This project was deleted at the November 2013 LMS meeting.
| Set aside a portion of "in lieu of taxes," funding received by the Franklin County School District from the Florida Division of Forestry, for a college forestry scholarship for students from Franklin County. | Wildfires | No | N/A | All jurisdictions in Franklin County. | N/A | N/A | This project was deleted at the November 2013 LMS meeting.
| Require flood hazard disclosure in a deed of sale or transfer of improved or unimproved of real property. | Floods | No | TBD | All jurisdictions in Franklin County. | Franklin County Building and Planning | N/A | This project was deleted at the November 2014 LMS Meeting.