## Sheet1
Priority | Description of Mitigation Project | Goal for Hazards Mitigated | Mitigation Goals Achieved | Funding Source | Jurisdiction (Location) | Agency Responsible for Implementation | Estimated Costs | Status |  |  |  | Timeframe to Complete
[8 empty] | New | Ongoing | Deferred | If Deferred Why?
The projects located in this color were completed mitigation projects (2015 - 2019). Selected projects were completed in previous years.
| Purchase and install a countywide telephone emergency notification system. | All Hazards | Yes | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management | In 2016 the Franklin County Sheriffs office discontinued the "Code Red" notification system. Franklin County Emergency Management has started using and maintaining Nixle. The State's notification system is now Everbridge. Nixle is a subsidiary of the Everbridge notification and alert Franklin has in place since 2017.
| Installation of hydrologic monitoring gauges on the Ochlocknee, Crooked, New and Apalachicola Rivers. | Floods | Yes | N/A | All jurisdictions in Franklin County. | Franklin County Emergency Management | The hydrologic monitoring gauges have been installed and the gauge installation at the Abercrombie Boat Ramp will occur once the ramp is rebuilt. The gauge has been purchased.
| Reduce flooding by replacing culverts and improving cross drains at Mill Road, McIntyre Road. | Floods | Yes | HMGP | All jurisdictions in Franklin County. | Franklin County Road Department | As of November 2012, the status of this stormwater project was the culverts were replaced and the improvement cross drain project was completed. The construction continued through 2013 and was funded through the HMGP.
| Build a new water well in Eastpoint. | All Hazards | Yes | N/A | Eastpoint | Eastpoint Water and Sewer District | A new water well was built in 2012. A secondary well was built and completed in 2017 at a cost of approximately $3,500,000.
| Upgrade a left station in the City of Apalachicola. | All Hazards | Yes | N/A | City of Apalachicola | Apalachicola Water and Sewer | In 2017, a lift station was upgraded with an installation of a new generator. The approximate cost was $150,000.
| Install Weather/ Water and Wind Gauges applied to all bridges and in various points around Franklin County. | All Hazards | Yes |  | All jurisdictions in Franklin County | Franklin County Emergency Management/ DOT/ Franklin County Sheriff's Office | In February 2017, FCEM has partnered with Weather Stem to place a weather reporting station on St. George Island fishing pier. DOT is looking into installing wind gauges on all bridges in the near future. Wind gauges have been placed and this project is completed.
| Institute Flag system/Display board for beaches. | All Hazards | Yes |  | All jurisdictions in Franklin County | DEP/FCEM/ Parks and rec State Park | Franklin County Parks and Rec has a flag system in place and is maintained by FCPR. There is 2 on St George Island and 1 in Carrabelle. They signage and information so that visitors are aware of the flag system. This project was completed in 2018.
| Install an updated water pump system in selected areas of Eastpoint. | All Hazards | Yes | CDBG | City of Eastpoint | Eastpoint Water and Sewer District | A new system and well on twin Lakes Road was completed in the 2012 - 2013 timeframe. In addition two new vacuum stations was completed. . The project will be completed in September of 2016. The Well#1 will be retired and they will begin using Well #4.
| Hurricane proof 34 Franklin County residential homes. | Hurricanes, tropical storms, severe thunderstorms, strong winds and tornadoes | Yes | HLMP | All jurisdictions in Franklin County. | Franklin County Emergency Management | There were 34 residential homes throughout Franklin County that were hurricane proofed through the hurricane loss mitigation program (HLMP).
| Mitigation on repetitive loss (RL) properties | Flooding | Yes | HMGP | All jurisdictions in Franklin County | Franklin County Emergency Management | As stated in the Flood Mitigation Assistance Plan, 52 RL properties were mitigation in recent years via relocation or acquisition/demolition.
| Emergency Operations Center (EOC) Wind Retrofit | All Hazards, Hurricanes, Tropical Storms, Tornadoes, and High Winds | Yes | HMGP | City of Apalachicola | Franklin County Emergency Management | A important project and a critical facility for Franklin County. The EOC was awarded a HMGP grant to complete the wind retrofit project. The project was completed in the 1st quarter of 2015. The project description: Protected the entire envelope of the Franklin County Emergency Operations Center by designing and constructing a new hip roof and installing high velocity accordion shutters on the windows and installation of a roll down shutter on the access door of the EOC. The total cost for the mitigation project was: $94,943.
| Franklin County Jail Wind Retrofit. | All Hazards, Hurricanes, Tropical Storms, Tornadoes, and High Winds | Yes | HMGP | Town of Eastpoint | Franklin County Emergency Management | A important project and a critical facility for Franklin County. In addition, the jail is a back-up facility for the EOC. The Franklin County Jail was awarded a HMGP grant to complete the wind retrofit project. The project was completed in the 3rd quarter of 2015. The project description: Installed a new retrofit Metal Frame/Metal Roof Assembly over the Jail’s Administration Building, and a new Membrane Roof System over the Jail Facility House. In addition provided protection of all windows and doors of the entire structure. The total cost for the mitigation project was: $729,267.
| Perform a study on the effects of severe hurricanes, high winds, tropical storms, tornadoes and storm surge on businesses that perform essential services to the community. | Hurricanes, Tropical Storms, Tornadoes, High Winds, and Storm Surge | No | TBD | All jurisdictions in Franklin County. | Franklin County Emergency Management | TBD | ARPC has communicated with FCEM and stated that this study has been completed
1 | Acquisition of Alligator Point Fire Department | All Hazards | No | HMGP | Alligator Point | Alligator Point St. Teresa Volunteer Fire Department / Franklin County Emergency Management | 402585.39 | The acquisition of the alligator point st. teresa fire department in currently in progress. |  |  |  | Within a one year timeframe
2 | 6 Critical Facilities Generators | All Hazards | No | HMGP | All jurisdictions in Franklin County | Franklin County Emergency Management | 842793 | Installation of the six generators for the County's critical facilities will be within the next year. |  |  |  | Within a one year timeframe
3 | Apalachicola, Market Street Vacuum Station, Utility Mitigation | All Hazards | No | HMGP/ CDBG-DR | City of Apalachicola | City of Apalachicola Water and Sewer Department/ Public Works Department/ Franklin County Solid Waste | 2333000 | Construction of a new vacuum sewage station near the intersection of Market Street and Avenue G. The project will upgrade the existing wastewater infrastructure and mitigate future occurrences of sanitary sewer overflows. |  |  |  | Within a one year timeframe
4 | Apalachicola, 2 Critical Facilities Generators | All Hazards | No | HMGP | City of Apalachicola | City of Apalachicola Administrator/ Franklin County Emergency Management | 303219 | Installation of the two generators for the City of Apalachicola's critical facilities will be within the next year. |  |  |  | Within a one year timeframe
5 | Apalachicola, Water Street Drainage | Flooding | No | HMGP | City of Apalachicola | City of Apalachicola Public Works Department / Administrator | 1626570.44 | There have been many storm flooding events that have caused considerable damage and especially to Water Street in the City of Apalachicola' s drainage. The goal is to have this mitigation project completed within the next two years. |  |  |  | Within a two year timeframe
6 | Update and enhance all communications equipment throughout the county | All Hazards | No | Grants/ BOCC/ Various Programs/ Local Funds | All jurisdictions in Franklin County | Franklin County Sheriff /Volunteer Fire Department/ Franklin County Emergency Management/ Road Department/ Solid Waste | Varies by project $5,000 to $500,000 | x | All Agencies are evaluating/ discussing options for interoperable communications throughout the county. Firenet is operational and this is an ongoing project for the County. |  |  | Within a five year timeframe
7 | Acquire, relocate or elevate repetitive damaged structures throughout the county. | Flooding, Storm Surge | No | HLMP/ HGMP | All jurisdictions in Franklin County | Franklin County Emergency Management | Varies as it depends on the type of structure |  | x |  | Funding | Within a five year timeframe
8 | Build a new EOC in a central location Franklin County possible location off of Hwy 65 | All Hazards | No | Restore/ BP /Franklin County BOCC | All jurisdictions in Franklin County. | Franklin County Emergency Management/ Franklin County Board of County Commissioners | 3000000 | Franklin County is looking at possible BP funds for building a new Multi-Agency Building. |  |  |  | Within a five year timeframe
9 | Retrofit the Old Carrabelle City Hall as a Volunteer Disaster Corp Training facility | All Hazards | NO | Private/ HMGP/ HLMP/ Non-profit funding | All jurisdictions in Franklin County | Franklin County Emergency Management/ Non-Profit Organizations | Varies by projects related to building | x | Various non-profits and county partners will be assisting with the work and funding for this project |  |  | Within a five year timeframe
10 | Construct a new Access Road at Franklin County School for Emergency Use | All Hazards | No | Grant/ HMGP/ Private funding | All jurisdictions in Franklin County | Franklin County Emergency Management | 300000 | Franklin County School and Forestry are constructing an access road through the forest for Emergency Access only to the facility. The Florida Forest Service has given consent for permitting/ Easement which was completed. At this time, this project is waiting for the School Board to construct Road. |  |  |  | Within a five year timeframe
11 | Purchase and install an oxygen filling station that can be utilized after a disaster. | All Hazards and Life Safety | No | Grant/ DOH | All jurisdictions in Franklin County | Franklin County Department of Health | 15000 | x | New Project for FLDOH - Hurricane Michael left a lot of residents with out access to oxygen. This project wants to be considered as a regional asset. |  |  | Within a five year time frame
12 | Carrabelle Fire Hydrant System extended to West Side of County located between the light house and yents bayou. | Wildfires | No | Grants/ Public/ Private | Carrabelle / Franklin County East | Carrabelle Fire Department/ City of Carrabelle Administration | 2500000 | x | Carrabelle Fire Department needs to install fire hydrants on the West side of Carrabelle to improve fire response to the county. This project is awaiting funding. |  |  | Within a five year timeframe
13 | Install Generators for all critical facilities, lift stations, government fueling depots located in Franklin County . | All Hazards | No | HMGP/ Grant / Private | All jurisdictions in Franklin County | Franklin County Board of County Commissioners/ City of Apalachicola/ City of Carrabelle | $100,000 to $500,000 | x | The project cost will vary depending on location and facility type. |  |  | Within a five year timeframe
14 | Acquire land and Construct new landfill | All Hazards, Environmental | No | BOCC funding /Grants/ HMGP | All jurisdictions in Franklin County | Franklin County Board of County Commissioners/ Franklin County Landfill | 1500000 | x | Franklin County Landfill is very limited. Franklin County Board of County Commissioners are looking for a new location for landfill expansion. |  |  | Within a five year timeframe
15 | Protect County Road 370 (Alligator Point Road) from hurricane storm surge. | Hurricanes, Tropical Storms, Storm Surge | No | FEMA funding | Unincorporated Franklin County - Alligator Point | Franklin County Road Department | 15000000 |  | x | Project is to move the road inland and acquire the RL properties. This mitigation project is deferred. |  | Ongoing
16 | Perform mitigation on efforts on residence homes against severe hurricanes, high winds , tropical storms, tornadoes and storm surge on low/moderate income owner occupied homes | Hurricanes, Tropical Storms, Tornadoes, Strong Winds, and Storm Surge | No | HLMP Funds | All jurisdictions in Franklin County | Franklin County Emergency Management | $200,000 yearly |  | x | Franklin County is currently working on a Hurricane Loss Mitigation Program for Franklin County residents. This is considered an ongoing project for the County and currently are awaiting funding for the fiscal year. As noted above, 34 homes were completed with the hurricane loss mitigation program in previous years.
17 | Reduce Coastal erosion by planting vegetation and participating in beach renourishment programs to the enhance the formation of sand dunes and to protect roads from washouts. | Coastal Erosion | No | FDEP Grant | All jurisdictions in Franklin County | Franklin County Emergency Management/ ANEER | Varies by projects ($10,000-$150,000) |  | x | This is ongoing project- FCEM and ANEER are working with several agencies to mitigate sand dunes and protect roads |  | Within a five year timeframe
18 | Florida Forest Service assess wildfire risk areas across the county establishing mitigation projects to measure the fuel loads and thus effectively reduce wildfire risk in these areas | Wildfires | No | Florida Forest Service | All jurisdictions in Franklin County and Alligator Point | Franklin County Emergency Management/ Florida Forest Service | Varies according to the risk area |  | x |  |  | Ongoing
19 | Construct a new Fire Station in Alligator Point. | All Hazards | No | HMGP/ HLMP/ Franklin County BOCC | All jurisdictions | Alligator Point St. Teresa Volunteer Fire Department / Franklin County Emergency Management | 2500000 | x | Location for new Fire Station has been identified and the old fire station can be purchased with HLMP as a repetitive loss structure. |  |  | Within a five year timeframe
20 | Work with the Florida Forest Service to update the Community Wildfire Protection Plan (CWPP) to reduce wildfire risks within the Wildland-Urban Interface. And inform the public of the Firewise building and landscape design principles and the Ready, Set, Go program. | Wildfires | No | Florida Forest Service | All jurisdictions in Franklin County | Franklin County Emergency Management/ Florida Forest Service | There is no cost for this mitigation project. | The CWPP for Franklin County was completed in 2013. The plan will be updated to reflect any current changes. The Florida Forest Service will continue inform the public of the Firewise building and landscape design principles and the Ready, Set, Go program. |  |  |  | Within a one year timeframe and ongoing.
21 | Protect and improve functioning of wetlands and waterways by eliminating and educating residents on living shorelines | Coastal and Riverine Erosion | No | Local funds | All jurisdictions in Franklin County | Franklin County Emergency Management/ ANEER | There is no cost for this mitigation project. |  | x | ANEER/FFS work together year round to locate/eliminate and improve the living shoreline through education and environmental projects. |  | Ongoing
22 | Update all County Mapping to include 911 overlay, flood prone areas, damage assessment, and property appraiser properties. | Flooding, Storm Surge | No | HMGP/ FCEM/ Various Funding | All jurisdictions in Franklin County | Franklin County Planning and Building/ Franklin County Appraiser's Office | 10000 |  | x | FCEM / Flood Plain Manager are working on systems that utilize the maps to identify all repetitive flood prone areas in ensure quicker emergency response time in the event of a disaster. |  | Ongoing
23 | Mitigate storm water drainage projects throughout Franklin county. | Flood, Storm Surge | No | Varies | All jurisdictions in Franklin County | Franklin County Board of County Commissioners/ Franklin County Planning & Building Department/ Cities of Apalachicola and Carrabelle Administrators | Varies by projects ($10,000-$750,000) |  |  |  | x | Within five year timeframe
24 | Develop and deliver Disaster Resistant programs for the business and residential communities on "how to prepare" for future disasters. | All Hazards | Yes | EMPA/ BOCC | All jurisdictions in Franklin County. | Franklin County Emergency Management | 15000 | Franklin County Emergency Management delivers ongoing programs and distributes materials on how to prepare for future disasters to the residential and business community. This is an ongoing project and FCEM will continue to educate all Franklin County Residents in being disaster ready. |  |  |  | Ongoing
25 | Raise areas of CR 67 to prevent road flooding. | Flooding | No | HMGP/ Private / BOCC | Franklin County | Franklin County Road Department | 3000000 |  | x |  |  | Within five year timeframe
26 | Wind Retrofit all Critical Facilities (including government and school facilities). | Hurricanes, Tropical Storms, Tornadoes, and High Winds | No | HMGP | All jurisdictions in Franklin County. | Franklin County Emergency Management/ Franklin County Board of County Commissioners/Franklin County School Board | Varies by location and type of structure; could be over $750,000 |  |  | x | Funding | Within a five year timeframe
27 | Relocation of the Apalachicola City Hall. | Flooding | No | HMGP/ Private funding | City of Apalachicola | City of Apalachicola City Administrator | 800000 | x | Apalachicola City Hall was damaged during Hurricane Michael and is located in a flood prone area. City is seeking to relocate out of the flood prone area. |  |  | Within a five year timeframe
28 | Upgrade or replace City and County Wastewater treatment facilities | Flooding | No | HMGP/ Private Funding / City of Apalachicola | City of Apalachicola | City of Apalachicola City Administrator/ Franklin County Solid Waste Department | 500000 | x | Apalachicola City Utilities needs improvements and upgrades on the current wastewater treatment center. |  |  | Within a five year timeframe
29 | Implement Community Rating System flood resilience activities. | Flooding | No | Local funds | All jurisdictions in Franklin County | Franklin County Board of County Commissioners/ Cities of Carrabelle and Apalachicola City Administrators/ Franklin County Emergency Management | Depending on the activity cost could range up to $30,000 | x | There will be future discussion on how to accomplish this activities. |  |  | Within a five year timeframe.
30 | Drainage Basin Analysis-Carrabelle/ Apalachicola and Unincorporated Franklin County | Flooding | No | Potential funding would be NWFWMD | All jurisdictions in Franklin County | Franklin County Board of County Commissioners/ City of Carrabelle Administrator/ Franklin County Building Department | 25000 | x | The scope of work for the analysis and study will need to be determined. |  |  | Within a five year timeframe
31 | Evaluate and mitigate all flood prone areas due to sand dune shift and other environmental factors. | Flooding | No | Potential funding would be FDEP grant | All jurisdictions in Franklin County. | Franklin County Board of County Commissioners/ City of Carrabelle Administrator/ City of Apalachicola Building Department | Depending on the area size the mitigating costs could be over $400,000+ | x | The scope of work will need to be reviewed and determined. |  |  | Within a five year timeframe
32 | Evaluate and mitigate all flooding prone areas throughout the County. | Flooding | No | Potential funding would be local funds | All jurisdictions in Franklin County. | Franklin County Board of County Commissioners/ City of Carrabelle Administrator/ City of Apalachicola Building Department | Depending on the area size the mitigation costs could range from $15,000 to over $1,000,000 |  |  | This project is deferred due to funding. |  | Within a five year timeframe.
33 | Work with the Florida Forest Service in offering forest protection education in the county's schools. | Wildfires | No | Florida Forest Service | All jurisdictions in Franklin County | Florida Forest Service | 200000 | Florida Forest Service (FFS) has secured a scholarship for $20,000 a year for a student who graduated from the Franklin County School to further education in Forestry. Agriculture class and FFS continually provides Forest Protection education to all Franklin County Students. During the Summer program 2 students spent 3 days a week working with the Forest Service. One Franklin County School student was given an $80,000 Scholarship. |  |  |  | Ongoing
34 | Conduct Community Emergency Response Team (CERT) training for the Franklin County residents. | All Hazards | Yes | Grants and Fund Raising | All jurisdictions in Franklin County | Franklin County Emergency Management | 15000 | Franklin County has a CERT group and continues to provide CERT training. This is an on-going program for the county. |  |  |  | Ongoing
35 | Improve efforts in debris removal of dead, dying or diseased trees and branches next to road and highways. | All Hazards | No | FDOT Funding/Duke Energy/ BOCC | All jurisdictions in Franklin County. | Franklin County Emergency Management/ Duke Energy/ State of Fl Contractor/ Road Department | Varies by project ($5,000 to $500,000) |  | x | Duke Energy maintains the power lines. State DOT Contractor maintains the Franklin County State highways. |  | Ongoing
36 | Work with the Florida Forest Service on evaluating the defensible space on all the critical facilities throughout the county. | Wildfires | No | Florida Forest Service | All jurisdictions in Franklin County | Franklin County Emergency Management/ Florida Forest Service | There is no cost for this mitigation project. |  | x | The Franklin County EM Director sent specifics to the local Florida Forest Service. The Florida Forest Service will provide the information on the defensible space on critical facilities. This is considered an ongoing mitigation project. |  | Ongoing
37 | Replace a control panel at a lift station in the City of Apalachicola. | All Hazards | No | City of Apalachicola | City of Apalachicola | City of Apalachicola Water and Sewer Department | 2500 | x | The City of Apalachicola is upgrading a lift station with an installation of a new control panel. The project is expected to be completed within two years. |  |  | Within a two year timeframe.
38 | Build a new wastewater treatment plant in Eastpoint. | All Hazards | No | City Funding | Eastpoint | Eastpoint Water and Sewer District | 3500000 |  | A new wastewater treatment plant in Eastpoint is currently being build. The estimated timeframe for completion is within two years. |  |  | Within a two year timeframe
39 | Educate the county residents on water saving techniques. | Drought | No | HMGP | All jurisdictions in Franklin County | Franklin County Emergency Management | The Emergency Management office will develop materials on water saving techniques that will benefit the county and citizens during a drought period. The estimated cost would to produce materials would be $500. |  |  |  |  | Within a two year timeframe
40 | Organize outreach to vulnerable populations including establishing and promoting accessible heating or cooling centers in the community. | Extreme Temperatures (heat waves and freezes) | No | There is no cost for this mitigation project. | All jurisdictions in Franklin County | Franklin County Emergency Management | The Emergency Management Department will devise an outreach program to reach the vulnerable populations throughout the County and promote safety and heating and cooling centers in the community. There would be no cost for this mitigation project. |  |  |  |  | Within a two year timeframe
41 | Install sirens at various points throughout the county. | Hurricanes, Tropical Storms, Tornadoes, Waterspouts, Strong Winds | No | BOCC | All jurisdictions in Franklin County | Franklin County Emergency Management | 5000 | Sirens are located a DW Wilson Park, Carrabelle RV Park and the Franklin County Schools. A maintenance plan will need to be developed and put in place. |  |  |  | Within a five year timeframe
42 | Enforce local laws, which allow local governments to enact burn bans during periods of drought. | Wildfire, Drought | Yes | There is no funding required. | All jurisdictions in Franklin County | Franklin County Board of County Commissioners | There is no cost for this mitigation project. | The county will continue to enforce the local laws to burn bans during periods of drought. |  |  |  | Ongoing
43 | Install tornado shelters throughout the county. | Tornadoes and Strong Winds | No | BOCC | All jurisdictions in Franklin County | Franklin County Emergency Management | 500000 |  |  | x | This project is deferred due to funding. | Within a five year timeframe
The mitigation projects in this color were deleted by the LMS Working Group.
| Retrofit the Carrabelle City Hall. | Hurricanes, Tropical Storms, Tornadoes, and High Winds | No | HMGP | City of Carrabelle | City of Carrabelle |  | This project was deleted at the August 2016 LMS meeting due to lack of funding for the possible relocation of Carrabelle City Hall. In addition in 2018 a new City Hall Complex was built.
| Inspect septic tanks for low-income homeowners and abate failing systems. | Floods | No | N/A | All jurisdictions in Franklin County. | N/A |  | This project was deleted at the November 2013 LMS meeting due to lack of funding.
| Purchase and install smoke alarms in low income homes. | Wildfires | No | N/A | All jurisdictions in Franklin County. | N/A |  | This project was deleted at the November 2013 LMS meeting. American Red Cross is completing this project.
| Set aside a portion of "in lieu of taxes," funding received by the Franklin County School District from the Florida Division of Forestry, for a college forestry scholarship for students from Franklin County. | Wildfires | No | N/A | All jurisdictions in Franklin County. | N/A |  | This project was deleted at the November 2013 LMS meeting due to lack of funding.
| Require flood hazard disclosure in a deed of sale or transfer of improved or unimproved of real property. | Floods | No | TBD | All jurisdictions in Franklin County. | Franklin County Building and Planning |  | This project was deleted at the November 2014 LMS Meeting due to lack of funding.
| Reduce flooding in the Rio Vista area by installing a drainage system on the north side of the road into Cow Creek and the Ochlocknee River. | Floods | No | TBD | All jurisdictions in Franklin County. | Franklin County Road Department/ Florida Forestry Service |  | This project was deleted due to lack of funding.
| Hwy 98 needs resurfacing from Carrabelle to Apalachicola. | All Hazards | No | FEMA/State Funded | All jurisdictions in Franklin County. | FDOT |  | Hwy 98 is a State Road - FDOT is evaluating the road and will be repaired from the damage from Hurricane Michael, therefore is was deleted.
| Reduce or prevent stormwater flooding in Apalachicola in the following areas: 24th and 25th Avenues, 8th through 10th Streets between J and G, and on US Highway 98 and 12th and 16th Streets. | Floods, Storm Surge | No | TBD | City of Apalachicola | City of Apalachicola Road Dept |  | This drainage improvement project is on the DOT 5-year capital project list. The DOT and Preble-Rish have agreed on a resurfacing project on US 98 through Apalachicola and estimated to be complete in 2014. The installation of buffer boxes are currently in progress. Some work has been done on 10th Street. The EM Director will get with the City and DOT for a status on the project. An update on the costs will be available at the next LMS meeting - Moved to deferred to adjust the new storm water projects
| Retrofit the FSU Marine Lab buildings. | Hurricanes, Tropical Storms, Tornadoes, and High Winds | No | HMGP | Franklin County and St. Teresa | FSU Marine Lab |  | FSU Marine Lab has other buildings that could benefit from a Wind Retrofit. Deleting this mitigation project until representative confirms that other buildings need retrofit.